Lessa?! | لسه؟

Smart Government Queue Tracking Platform

2-Day Hackathon Sprint Plan

Version 1.0 — Hackathon MVP Edition  |  June 2026

Team of 3  |  48 Hours  |  Version 1.0 MVP Delivery

# 1. Delivery Strategy

2-day hackathon sprint. Goal: a fully demo-able MVP with real data, functional queue operations, and an AI prediction showcase. The strategy is to work in three parallel workstreams (Backend, Frontend, and Data/DevOps/AI) with integration checkpoints at end of Day 1 and mid-morning Day 2.

# 2. Assumptions

- Team of 3: one backend-heavy (BE), one frontend-heavy (FE), one full-stack/devops (FS)

- React + Node/Express + PostgreSQL tech stack agreed before Day 1

- Development environment (Node, Postgres, Redis) configured before Day 1 begins

- Repository initialized with monorepo structure; CI not required for MVP

- Demo environment (Render or Railway) accessible and tested before Day 1

- Seed data script will be pre-written before demos begin

# 3. Critical Path

DB Schema → Backend Auth → Backend Booking → Backend Queue Engine → Integration Test → Supervisor + AI + Display Board → Demo Rehearsal

# 4. Team Assignments

| Member | Role | Primary Responsibility |
| --- | --- | --- |
| Engineer A | Backend | Auth, Booking Module, Queue Engine, Notifications, Queue Rules |
| Engineer B | Frontend | Citizen App, Staff Interface, Supervisor Dashboard |
| Engineer C | Full Stack + AI | DB migrations, Prediction Engine, Public Display Board, Reports, Seed Data, Deployment |

# 5. Day 1 Plan — Hours 0–12

Day 1 goal: Core booking → queue → calling flow working end-to-end. All critical path stories complete.

| Hour | Engineer A (Backend) | Engineer B (Frontend) | Engineer C (Full Stack + AI) |
| --- | --- | --- | --- |
| 0–1 | Finalize tech stack, set up repo, branch strategy | Same as BE | DB schema design + migration files |
| 1–3 | Auth module: register, OTP mock, JWT, RBAC middleware | React app scaffold: Vite + Tailwind + shadcn/ui, routing, i18n setup | Run migrations; seed: 1 branch, 3 services, 3 windows, 5 users |
| 3–5 | Service Catalog API: CRUD + public list with queue stats | Citizen: Registration + Login screens | Prediction Engine: heuristic formula + prediction API endpoint |
| 5–6 | Booking Module: POST /tickets (atomic sequence, validations) | Citizen: Service List page (public) | Public Display Board: page + API endpoint |
| 6–7 | Queue Engine: call-next, resolve, grace period timer | Citizen: Booking flow + Ticket confirmation screen | SSE infrastructure setup |
| 7–8 | Notification Module: create notifications on state changes | Citizen: My Ticket + real-time position display | Connect SSE to Frontend |
| 8–9 | Window Module: open/close/pause, staff-window assignment | Staff Interface: Window dashboard + Call Next button | Deploy to Render/Railway; verify environment |
| 9–10 | Integration testing: booking → queue → call → resolve | Staff Interface: Done/Skip/No-Show actions | Supervisor Dashboard: live window grid |
| 10–11 | Bug fixes from integration testing | Notification bell + in-app notification list | Reports API: daily-summary, peak-hours |
| 11–12 | Cancellation + modification flow; cancellation cutoff | Supervisor: Reports page + Announcement form | Admin Panel: user management + queue rules config |

# 6. Day 2 Plan — Hours 13–24

Day 2 goal: Polish, QA, AI prediction, display board, demo prep, and final deployment.

| Hour | Engineer A (Backend) | Engineer B (Frontend) | Engineer C (Full Stack + AI) |
| --- | --- | --- | --- |
| 13–14 | Bug fixes from Day 1 testing | Admin Panel: User creation + role assignment | Seed realistic demo data (100+ tickets across 2 hours) |
| 14–15 | Turn-approaching notification trigger | Public Display Board polish: large font, animations | Prediction snapshot storage (async) |
| 15–16 | Audit logging: complete coverage of all critical actions | Supervisor: Announcement posting + display | Historical factor computation from seeded data |
| 16–17 | End-to-end QA pass (all user flows, all roles) | Mobile responsiveness pass + RTL Arabic layout | QA: Arabic UI, RTL layout check, display board |
| 17–18 | Fix QA issues | Fix QA issues | Verify deployment; run load test (10 concurrent bookings) |
| 18–19 | Demo Prep: demo accounts, walk-through script | Demo polish: loading states, error messages, animations | Prepare demo video backup (screen recording) |
| 19–20 | Stretch: QR check-in mock or predicted wait countdown | Stretch: Animated ticket call display on display board | Stretch: Historical chart on reports page |
| 20–21 | Final demo rehearsal (all 3 together) | Final demo rehearsal | Final demo rehearsal |
| 21–24 | Buffer: remaining bugs, final deploy, presentation prep | Buffer | Buffer |

# 7. Must / Should / Could Feature List

| Priority | Feature | Owner |
| --- | --- | --- |
| Must | Citizen registration + login | BE + FE |
| Must | Service list (public) | BE + FE |
| Must | Book a queue slot | BE + FE |
| Must | Staff: Call Next + resolve ticket | BE + FE |
| Must | Real-time ticket tracking (SSE or polling) | BE + FS + FE |
| Must | AI predicted wait time | FS |
| Must | Public display board | FS + FE |
| Must | Supervisor dashboard | FE + BE |
| Must | In-app notifications | BE + FE |
| Must | Arabic + English UI | FE |
| Should | Cancel/modify booking | BE + FE |
| Should | Turn-approaching notification | BE + FE |
| Should | Daily summary report | BE + FE |
| Should | Branch announcement | BE + FE |
| Should | Admin user management | BE + FE |
| Should | Audit logs (admin view) | BE + FE |
| Could | Predicted wait countdown animation | FE |
| Could | Animated display board transitions | FE |
| Could | Peak hours chart | FE |
| Could | Window performance report | BE |
| Could | Prediction snapshots + accuracy tracking | FS |

# 8. Risk Mitigation

| Risk | Mitigation |
| --- | --- |
| SSE too complex → use polling | Pre-decide: if SSE setup takes >1 hour, switch to 30-second polling |
| RTL layout breaks | Test Arabic UI at Hour 3 (not Hour 18); use CSS logical properties from the start |
| Queue race condition hard to debug | Write atomic DB query (SELECT FOR UPDATE) and test with 2 concurrent bookings early |
| Prediction gives nonsensical values | Clamp output to 0–240 minutes; show "N/A" if computation fails |
| Deploy fails on PaaS | Test deploy at end of Day 1; maintain fallback (localhost demo) |
| Seed data looks unrealistic | Pre-write seed script before Day 1; use realistic Egyptian names, Arabic service names |

# 9. Testing Strategy

| Level | What | When |
| --- | --- | --- |
| Unit | Prediction engine formula, ticket status transitions | Inline with dev; 30 min total |
| Integration | Booking flow end-to-end, concurrent booking (race condition), queue calling | End of Day 1 |
| Manual QA | All 5 user roles, both languages, mobile viewport | Day 2 Hours 16–17 |
| Load test | 10 concurrent bookings against last slot | Day 2 Hour 17 |
| Demo rehearsal | Full scenario walkthrough (all roles) | Day 2 Hours 20–21 |

# 10. Demo Preparation Checklist

| Item | Details | Status |
| --- | --- | --- |
| Admin account | phone: +201000000000 | ☐ |
| Counter staff accounts | staff1, staff2 with window assignments | ☐ |
| Supervisor account | supervisor1 assigned to Cairo Central Branch | ☐ |
| Citizen accounts | 5 accounts with realistic Egyptian names + Arabic variants | ☐ |
| Services seeded | NID (National ID), PASS (Passport), BC (Birth Certificate) | ☐ |
| Windows open | 3 windows open and assigned to staff | ☐ |
| Historical tickets | 50–80 tickets across services with mixed statuses (done, no-show, waiting) | ☐ |
| Live demo tickets | 5 tickets in "booked/waiting" for live demo flow | ☐ |
| Branch announcement | Pre-drafted announcement ready to post during demo | ☐ |
| Arabic UI ready | Switch to AR locale; verify RTL layout | ☐ |
| Display board tab | Open on second screen/tab for demo | ☐ |
| Screen recording | Backup recording prepared in case of connectivity issues | ☐ |
| Demo script | Printed/rehearsed walkthrough covering all 5 roles | ☐ |

# 11. Seed Data Reference

The following SQL snapshot captures the minimum seed data required for a convincing demo. Run this before any demo session.

-- Branch INSERT INTO branches (id, name, name_ar, address) VALUES ('branch-01', 'Cairo Central Branch', 'فرع القاهرة المركزي', '12 Tahrir Square, Cairo'); -- Services INSERT INTO services (code, name_en, name_ar, avg_handling_time_minutes, daily_capacity, branch_id) VALUES ('NID', 'National ID Renewal', 'تجديد بطاقة الرقم القومي', 5, 100, 'branch-01'), ('PASS', 'Passport Services', 'خدمات جواز السفر', 8, 80, 'branch-01'), ('BC', 'Birth Certificate', 'شهادة الميلاد', 4, 60, 'branch-01'); -- 80 historical tickets (yesterday, status: done) for AI historical factor -- 5 active tickets today (status: waiting) for live demo -- 1 announcement: "System working normally. Thank you for your patience."

# 12. Recommended Technical Defaults

These implementation defaults resolve known ambiguities before coding begins:

| Decision | Recommended Default | Reasoning |
| --- | --- | --- |
| OTP Provider | Mock: static code 123456, stored in env | Zero cost, zero complexity, demoable |
| Real-time mechanism | Start with polling (30s); add SSE for display board | Display board SSE is low risk; citizen polling is good enough |
| Redis | Optional; use JS Map in-memory for queue state | For single-server MVP with <200 concurrent users, JS Map is fine |
| Frontend structure | Single React app, role-based routing + layouts | Fastest to build; shared component library |
| Grace period timer | setTimeout + DB update for MVP | Simple; replace with pg-boss post-MVP |
| Check-in requirement | Optional; booked → waiting at position recalc | Reduces citizen friction |
| Queue position calc | Lazy calculation on read; cache in memory per service | Avoids DB hammering; acceptable for MVP scale |
| Display board refresh | SSE from same endpoint as citizen tracking | Reuses SSE infrastructure |